 **Currently Active Capital Improvement Projects**

|  |  |
| --- | --- |
| Town Hall | Under contract. Phase 1, preliminary designs, complete. Phase II, construction drawings and final budget, winding down. Phase III, construction expected to begin this summer. |
| Public Works Building | Site Prepared. RFQ published on 3/4, closes on 3/29, informational meeting on 3/18. |
| Texas Rd. Pedestrian Bridge | RFQ for design services closed on 2/11. Contract negotiations underway with Vaughn & Melton. |
| Texas Rd. Waterline | Expected completion date 3/21 |
| Texas Rd. and Calvin Trail Paving | Project awarded in the fall ‘18- expected completion in early spring |
| Frist Rd. Paving | Project awarded in the fall ‘18- expected completion in early spring |
| Wells A & B Chlorine Retrofit | In process. Expected completion date 4/4. |
| Well 6 Pump Conversion | In process. Expected completion date 3/21. |
| Assembly Drive Culvert and Crosswalk | In process. Expected completion date 3/18. |
| Tennessee Rd. Culvert and Catch Basin | In process. Expected completion date 3/21. |
| South Carolina Terrace Parking Area | Engineer assessed - Expected completion 4/4. |
| Kentucky Rd. Culvert | Engineer assessed - Expected completion date 4/25 |
| South Carolina Terrace Culvert | Engineer assessed - Expected completion date 4/11 |
| Wyck Rd. Culvert | Engineer assessed - Expected completion date 4/18 |
| Lower Greybeard Wall and Creek Stabilization | RFQ re-published on 2/28, closes on 3/20. |
| Suwannee Mudslide | Engineer assessed - RFQ pending. |
| Texas Road Extension Culvert and Barrel -1 | Engineer assessed - RFQ pending. |
| Texas Road Wall and Bank Stabilization (Below Pool) | Engineer assessed - RFQ pending. |